## Feedback tracking
# | Original feedback (verbatim) | What's done | How to test | Status
1 | We should review the columns as per the current live version. things like email verified, linkedin verified also need to be there, maybe it can be consolidated into a verification column but whatever be the case we should make sure its aligned with whatever we want to keep from the live version so that there is no confusion | Verification column shows email + linkedin badges with status tooltip. Columns picker exposes 13 columns: Name (pinned), Title, Company, Location, Verification, Work Email, Phone, Score, Outreach, Sequence, Source, Last activity, Segment. Default 8 visible; user toggles the rest. | Leads tab → confirm 8 default columns. Hover Verification badges to see email + linkedin tooltips. Click Columns button → toggle Work Email / Phone / Sequence / Source / Last activity on. Show all → Hide all → Reset returns to default 8. | DONE
2 | Should we introduce A/B testing at this stage ya first clean up segments as per the new flow? if no, lets remove that step | A/B step removed entirely from creation panel. Panel now has 5 steps: Name → Audience → Message → Senders → Preview. | Click + New segment → stepper shows exactly 5 steps with no A/B step anywhere. | DONE
3 | say I create segment of a sublist of users and then start the outreach. if I want to create further segments and start the outreach for those, how to do that? its not entirely clear | Per-segment launch state (draft / live / paused / done). Each segment has its own Launch / Pause / Resume button in the Segments tab and Live tab. Campaign state derives from per-segment statuses. Header counts show N live · N paused · N draft. | Launch Senior Leaders → it goes Live, header shows 1 live. Create a second segment, leave as Draft. Go to Segments tab → click Launch on the second → both Live, header 2 live · 0 paused · 0 draft. | DONE
4 | adding to the above, we should also make it clear why users already being reached out via an existing segment cannot be added, or say why I cant trigger another outreach for the same segment if its already live. | Row kebab on an in-outreach lead shows lock message: 'Moving could cause duplicate messages. Pause the segment first to make changes.' Same lock extended to Selection toolbar (orange chip + actions disabled when all selected are locked). Segments tab: Edit on a Live segment locks the Audience step with explanatory banner (Name / Message / Senders editable). Delete on Live row disabled with tooltip 'Pause the segment before deleting it.' | Launch Senior Leaders. Leads tab → kebab on Dan Fetzer (outreachStarted) → lock message, no move/unassign options. Tick him + an Unassigned lead → toolbar shows orange '1 in active outreach (locked)' chip. Tick only in-outreach leads → all action buttons hidden, lock explanation shown. Segments tab → Edit on Live Senior Leaders → Audience step locked banner; Delete disabled. | DONE
5 | In the live tab, the per segment progress has a chevron button but it does not do anything. | Chevron now expands the segment row to show a per-step funnel: each step's reach / opened / replied with percentages. | Live tab → click chevron on a live segment row → row expands to show per-step funnel. | DONE
6 | How does the live tab look like when I have triggered outreach for 1/3 segments that I created? | Live tab renders one row per segment. Live = pulsing green dot, lead count, sequence name, progress bar, sent/opened/replied counts, Pause button. Draft = grey dot + 'Not launched yet' + coral Launch button. Paused = amber dot + Resume button. | Create 3 segments, launch only 1. Go to Live tab → 1 row with pulsing green + counts, 2 rows in Draft state with Launch buttons. Click Launch on a draft row directly from Live tab → it goes Live. | DONE
7 | how to edit a segment already created (but ofcourse not yet activated for outreach)? What if I want to change the senders used, or change the outreach sequence | Segments tab → Edit button per row. Opens creation panel in edit mode with all fields pre-filled. Stepper is fully clickable so you can jump straight to Senders or Message. Footer reads 'Save changes' instead of Continue/Create. For Draft segments everything is editable; for Live segments the Audience is locked but Name / Message / Senders remain editable. | Segments tab → Edit on a Draft segment → all fields pre-filled. Jump to Senders step → switch to 'Segment-specific' → pick a subset of senders → Save changes. Segments table reflects the new sender mode. Repeat for Message step to swap sequence. | DONE
8 | User should be able to manually select leads for assigning segment without requiring the audience selection and directly select sequence | Selection toolbar appears when any lead checkbox is ticked. 'Create segment from these' opens panel skipping the audience filter sidebar; selected leads are locked as the audience. Flow: Name → (locked audience) → Message → Senders → Preview. | Tick 4 lead checkboxes → toolbar appears. Click 'Create segment from these' → panel opens at Audience step with locked list (no filter sidebar). Continue → Message → Senders → Create. Confirm segment has exactly those 4 leads. | DONE
9 | Add option to create new sequence (Current options: Close Existing; Use Existing; AI Generated) | Message step now offers 4 sources: Use existing / Clone & edit / Generate with AI / + Create from scratch. Scratch path starts with empty Step 1 + 'Add step' button. Two-pane editor (steps left, preview right) for all paths. | New segment → Message step → see 4 cards. Pick '+ Create from scratch' → editor opens with one empty step + Add step at bottom. Add steps, write content, advance. | DONE
10 | How can I view sequences/leads/senders under each existing segment? Can we bring back the segments tab? | Segments tab restored. Table columns: Segment / Type / Leads / Message flow / Senders / Status / Actions. Each row shows the sequence name + step count, sender mode + count, real Status pill (Draft/Live/Paused/Done). View button jumps to Leads tab filtered to that segment. | Segments tab → confirm 7-column table with sequence info + sender info + status visible per row. Click View on Senior Leaders → switches to Leads tab pre-filtered to that segment. | DONE
11 | Allow user to manually unassign a lead out of a segment later | Row kebab on a lead currently in a custom segment shows 'Unassign' option below the 'Move to' list. Sends the lead back to the Default (Unassigned) segment. Locked behind the active-outreach check so in-flight leads can't be silently unassigned. | Move a lead to Senior Leaders. Click kebab → Unassign → lead returns to Unassigned chip. (Note: a separate bug — feedback #17 — needs to be investigated for the Move-to direction.) | DONE
12 | In the audience selection section, can we add multi-select option for keywords. Currently for any filter eg: role contains - I am not able to add more than one keyword | ChipInput component on all keyword filters (Title contains, Company name contains). Press Enter or comma to add. OR-within-field (any chip matches), AND-across-fields (every filter must match). | Audience step → Title contains → type 'CFO' Enter → 'VP' Enter → see two coral chips, matched count expands. Add a Company name chip → matched count narrows (AND across fields). | DONE
13 | Add these filters in audience selection section: Company Name, Profile Verification | Both filters added to Audience sidebar. Company name uses ChipInput with substring match across full company name. Profile verification = Any / Email verified / LinkedIn verified / Both verified. | Audience step → type 'Aspen' in Company name → matches Aspen Pharma Group + Aspen Pharmacare. Profile verification → Both verified → narrows further to leads with both badges green. | DONE
14 | Can we also add the campaign summary/overview as well as activity part? Recommendation to maybe merge "Live" and "Analytics" section together. | Campaign header strip below the campaign name shows: '12 companies · 28 contacts · N in outreach · M sent today · P% reply rate · N live · N paused · N draft'. Counts derive from segments + leads and update live. Live + Analytics not merged (kept separate — happy to merge if you still want). | Look at header strip below campaign name. Pause / Resume a segment → header counts update in real time. | PARTIAL
15 | Add more senders to test. so we can test specific senders as well | data.ts pre-seeds 4 senders in Configured mode: sharan@, anoothi@, careers@, hello@. First-run mode stays empty. Settings 'Add a mailbox' / 'Add another' cycles through senderPool, then falls back to mailbox-N@lumif.ai. Segment-specific sender mode in the creation panel now has senders to choose from. | Settings tab → see 4 seeded mailboxes. Demo switcher → First-run → Settings shows 0 + 'Add a mailbox' CTA → click → one added → click 'Add another' → next from pool appears. Back to Configured → New segment → Senders step → 'Segment-specific' → checkbox list of 4 senders. | DONE
16 | Duplicated segment names should not be allowed - show error / warning | SegmentCreationPanel.canAdvance() rejects names matching an existing segment (case-insensitive, excludes current edit). Inline warning with AlertCircle icon + red border on the Input. Continue button disabled while error stands. | New segment → type 'Senior Leaders' (already exists) → red warning 'A segment named "Senior Leaders" already exists' + Continue disabled. Type 'Senior Leaders 2' → warning clears. Edit existing 'Senior Leaders' → editing keeps its own name (not flagged against itself). | DONE
17 | Move an Unassigned lead to Senior Leaders -- Lead's Segment cell updates, Senior Leaders count +1, Unassigned count -1 -- This is not working / Everything goes to unassigned | Not yet fixed. Code-trace of moveLead in App.tsx looks correct logically; couldn't reproduce from code alone. Strong hypotheses: (a) user filtered chip to 'Unassigned' first, so moved lead disappears from the filtered view (works, but looks like nothing happened), or (b) user moved via Selection toolbar which had a separate bug — that path is now also fixed defensively (item #18), so re-test will tell us which. | Pick an Unassigned lead (e.g., Dilson Fernandes). Active segment chip = 'All'. Click kebab → Move to Senior Leaders. Expected: Segment cell shows Senior Leaders, top-chip counts update (Senior Leaders +1, Unassigned -1). If still broken, screenshot the row + chips and share so we can pin it down. | DEFERRED
18 | Kebab on a lead in active outreach blocks moves correctly. But the selection toolbar (top menu above the table) allows the same lead to be moved | SelectionToolbar gets a leads prop and computes lockedIds (outreachStarted === true). Composition row shows orange 'N in active outreach (locked)' chip. When ALL selected are locked, Move-to / Add-to / Create / Launch are hidden and the toolbar shows an explanation instead. App.addLeadsToSegment defensively filters outreachStarted leads so even programmatic calls skip them. | Launch Senior Leaders. Leads tab → tick a mix of in-outreach + unassigned leads → toolbar shows orange lock chip. Move-to still works on movables only. Tick ONLY in-outreach leads → all action buttons hidden, lock message shown. | DONE
19 | (Side issue caught during testing) Column-header filter Clear button is hidden once a filter is applied | ColumnHeaderFilter popover now renders via React portal with position: fixed. Coordinates computed from the trigger's bounding rect on open + on scroll / resize. Right-edge collision flips the popover to right-aligned (fixes Location column). Bottom collision flips above the trigger. | Apply Company filter (e.g., select Aspen Pharma Group) → close → reopen → 'Clear filter' button now fully visible at bottom. Open Location filter (rightmost) → popover stays inside viewport. | DONE

## Legend
Status | Meaning
DONE | Implemented + verified in code. Ready to test.
PARTIAL | Core ask shipped, optional sub-ask deferred. Ready to test what's done.
DEFERRED | Not yet investigated / fixed. User asked to defer.
OPEN | Known bug, awaiting fix.